## Sheet1
TASK TYPE | TASK NAME | ETA | Description
Update SDK | Research and Documentation | 1d | Research Android SDK 33 changes and updates. Document the list of changes and updates relevant to the game
| Update Idle Pirate | 1.5d
| Update Idle Highschool | 1.5d
| Update Idle Factory | 1.5d
| Update Idle Mail | 1.5d
| Update Idle Taxi | 1.5d
| Update Idle Farm | 1.5d
| Update Idle Family | 1.5d
Mini map game | Research Game Source Code | 3d | Study the source code and design patterns used in the original game
| Design Cat Rescue Event | 1d | Design the user interface for the Cat Rescue event.
| Implement Cat Rescue Event Mechanics | 4d | Develop the game logic for the Cat Rescue event. Create a system to track and sum the cash earned from clicking on cats during the event
| Implement Event Timing and Rules | 3d | Implement the daily event timing, including start and end times. Handle event restarts for the new day. Implement the rule set for event participation based on user activity
| Implement Win/Fail Cases | 3d | Implement the logic for event completion and failure scenarios. Create the reward pop-up with options to collect or multiply by watching an ad
| Data Tracking and Analytics | 5d | Implement tracking of session time and session count for event completion. Track user progress and the number of cats collected. Implement tracking for user choices between collecting and watching ads
| Localization | 2d | Implement text localization for the Cat Rescue event
| Total | 31d